## Test Scripts-ACH
UAT Test Case – Transaction Monitoring Model Weekly Threshold (ACH transfers)
Test Case ID | Scenario | Pre-Conditions | Steps | Expected Result | Actual Result | Status (Pass/Fail) | Comments
AML-001 | Validate Alert for High value ACH Transfer | TM model configured with threshold >$10,000 in a week | 1. Load the test data with multiple transactions from same customer | Alert generated for ACH transfer | Alerts triggered | Pass
2. TM generated alert for ACH > $10,000 in a week
3.Check TM triggers both ACH credit and ACH debit are alerted
4.verify alerts
AML-002 | Validate no alert for cumulative transactions below $10,000 in a week | TM model configured with threshold >$10,000 per week | 1. Load the test data with multiple transactions from same customer cumulating $3,000 in a week | No alert generated for customers with total transactions under $10,000 weekly. | No alerts | Pass
2. Run the model
3.no alerts
AML-003 | Test model sensitivity when threshold is adjusted | Update model threshold to $8,000 per week | 1. Modify configuration file or parameter | alerts generated; system responds correctly to threshold change. | Alerts triggered with modified threshold | Pass
2. Rerun model on same data
3. Compare new alerts
AML-004 | Validate ACH transaction data accuracy between source and TM model | Compare and validate source and TM | 1. Extract ACH transaction records from source system for the test period.
2. Extract same records from TM table
|  |  | 3. Compare key fields — transaction ID, account number, routing number, amount, date, and status | Should be 100% match no mismacthed records | No mismatch found | Pass
4. Identify any mismatches
AML-005 | Validate completeness of ACH data load (no missing or duplicate records) | Source dataset contains defined number of ACH transactions | 1. Count total ACH transactions in source system. | Records should match source system and TM model | Record match found | Pass
2. Count total loaded into TM model.
3. Run duplicate check on transaction IDs in target table
4. Compare counts and identify missing or duplicate entries
AML-006 | Validate data completeness for cumulative transaction logic | Source data available for full 7-day period | 1. Check transaction counts per customer in input and model tables | 100% data integrity maintained; no missing transactions. | Condition satisified | Pass
2.Verify all transactions included in cumulative calculation

## Test Scripts-P2P
UAT Test Case – Transaction Monitoring Model (P2P transfers)
Test Case ID | Scenario | Pre-Conditions | Steps | Expected Result | Actual Result | Status (Pass/Fail) | Comments
AML-001 | Verify alerts for frequent P2P in/out | Transactions loaded for 7 days | 1.Validate genertaed alerts has frequent p2p in and out using SQL query. | A001 flagged | flagged | Pass | As expected
AML-002 | Change threshold count=6 | Same data | Update SQL parameter | No alert generated | No alert generated | Pass | Model behaves as expected
AML-003 | Verify incorrect data handling | Inject duplicate TXN | Run validation SQL | Duplicate detected | Duplicate detected | Pass | Validation working